Annex 9

| Activity |  | Description of activity | Persons in charge / Attendants |  |  |  |  | Deadline | Input documents | Output documents |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | JTS | Head of FLCU | First level controller(s) | Project partner | Officer in charge with errors |  |  |  |
|  | Sub-activity 1.1 | The Head of the FLCU, assigns controllers in charge with the first level control for each partner |  | X | X |  |  | 5 working days after submission of the first partner report | ► List of the project partners | ► List of the persons in charge with the first level control for every partner |
| 1. Submission of the reports by the partners to the FLCU | Sub-activity 1.1 | Each project partner shall submit through JeMS to the FLCU a report regarding the implementation of the project in the required format at the end of the reporting period stipulated by the subsidy contract. This report shall contain all documents relating to expenditure incurred by the partner in this period, including the accounting documents. |  |  | X | X |  | The deadline stipulated in the subsidy contract | ► The application form ► Partner report of the partner (Annex 2) ► List of expenditure (Annex 3) ► Supporting documents pertaining to respective partner’s reports |  |
|  | Sub-activity 1.2 | Registration of the submitted report (In/out register and/or electronic database) |  |  | X |  |  | The same day with the reception of the report | ► through JeMS | ► Registry for FLC requests (Annex 1) |
| 2.Verification of the reports submitted by the partners based on the relevant documents | Sub-activity 2.1 | The controller carries out the verification of the report filled by the partner. The control is performed administratively, financial and technically by filling the check lists. |  |  | X |  |  | Total of 60 days allocated for all activities | ► Partner Report (Annex 2) ► List of expenditure (Annex3) ► Supporting documents pertaining to respective partner’s reports | ► FLC Checklist (Annex 6) ► FLC Report (Annex 7) ► FLC Certificate (Annex 8) |
|  | Sub- Activity 3.2 | In case expenditure related to work contract is reported FLC send request for support by the External Technical Expertise Company hired by BRCT Timişoara in maximum 10 calendar days upon receiving Progress report. |  |  | x |  |  |  |  |  |
|  | Sub-activity 3.3 | The verification of the report and the filling of the checklist by another controller |  |  | X |  |  |  |  |  |
|  | Sub-activity 3.4 | If the partner's report is not complete or contains administrative/financial/ technical errors the controller will require amendments/clarifications/corrections of the relevant parts of the report |  |  | X |  |  |  |  | ► Letter for requiring amendments/clarifications/ corrections (Annex 4) |
|  | Sub-activity 3.5 | The partner makes in 5 working days the amendments/clarifications/ corrections and submits them together with the support documents |  |  |  | X |  |  | ► Letter for submitting amendments/clarifications/ corrections received by the partner ► Amendment/ clarification/ correction of the report and the supporting documents |  |
|  | Sub-activity 3.6 | The controller performs the verification of the additional information / clarifications / corrections and the supporting documents filled in by the partner. Following the reception of clarifications from partner, if partner’s report still contains administrative, financial or technical errors, the controller is entitled to request again from them, and for the last time, the additional necessary documents/ clarifications/ corrections of relevant parts of report as deemed appropriate. |  |  | X |  |  | Total of 60 days allocated for all activities The deadline is suspended in case the FLC sends out requests for clarification to the project partners and resumes when the answers are received. | ► Amendment/ clarification/ correction of the report and the supporting documents | ► FLC Checklist (Annex 6) ► FLC Report (Annex 7) ► FLC Certificate (Annex 8) ► Letter for requiring amendments/clarifications/ corrections (Annex 4) |
|  | Sub-activity 3.7 | The partner provides, in 5 working days, for the 2nd time the required additional information / clarifications / corrections and submits them together with the supporting documents |  |  |  | X |  |  | ► Letter for submitting amendments/clarifications/ corrections received by the partner ► Amendment/ clarification/ correction of the report and the supporting documents |  |
|  | Sub activity 3.8 | The controller performs the verification of the additional information / clarifications / corrections and the supporting documents filled/uploaded by the partner. |  |  | X |  |  |  |  | ► FLC Checklist (Annex 6) ► FLC Report (Annex 7) ► FLC Certificate (Annex 8) |
|  | Sub activity 3.9 | In case of the partner not submitting the required documents/clarifications requested, the related unjustified expenditure is not getting approval and as such is reduced from total value of expenditure claimed. |  |  | X |  |  |  |  | ► FLC Checklist (Annex 6) ► FLC Report (Annex 7) ► FLC Certificate (Annex 8) |
|  | Sub-activity 3.10 | If, during the verification made based on the supporting documents, an irregularity is found it shall be reported and handled according to the national procedures. |  |  | X |  |  |  | ► Partner's report ► Additional information / clarification/ correction of the report and the supporting documents | ► Letter for notifying the irregularity |
| 4. Verification on-site | Sub-activity 4.1 | On site visits to be performed at all projects according with the FLC Guide. |  |  | X | X |  | Serbian FLC and Romanian FLC have the obligation to visit all the partners when in the reporting period works or goods have been delivered (except when in the reporting period the office supplies and stationary have been delivered), or at least once in the course of project’s lifetime | ►The application form ►The subsidy contract ► Partner's report ► Additional information / clarification/ correction of the report and the supporting documents |  |
|  | Sub-activity 4.2 | The partner is notified regarding the date of the visit on site ( fax or mail) |  |  | X |  |  | 1 working day | ► Partner’s progress report | ► Notification letter (Annex 5) |
|  | Sub-activity 4.3 | The on-site visit is done, containing all the findings, are drawn up |  |  | X | X |  | at the date agreed on with the partner | ► The subsidy contract; ► The supporting documents checked on site | ► FLC Checklist (Annex 6) ► FLC Report (Annex 7) ► FLC Certificate (Annex 8) |
|  | Sub-activity 4.4 | If, during the verification made based on the supporting documents, an irregularity is found it shall be reported and handled according to the national procedures. |  |  | X |  | X | 5 working days from the identifying irregularities | ► The supporting documents | ► The notification letter |
| 5. Decision regarding the eligible expenditure | Sub-activity 5.1 | Based on the findings and as a result of the control made based on the documents and the verifications on-site, if the partner's report is correct from the administrative, financial and technical point of view, the controller establishes the value of the eligible expenditure |  |  | X |  |  | 60 days | ► The partner's report; ► The subsidy contract; ► The supporting documents to the report | ► FLC Checklist (Annex 6) ► FLC Report (Annex 7) ► FLC Certificate (Annex 8) |
|  | Sub-activity 5.2 | The final value of the eligible expenditure and the check lists of the report are filled by the second controller |  |  | X |  |  | 60 days | ► The partner's report; ► The subsidy contract; ► The additional documents to the report | ► FLC Checklist (Annex 6) ► FLC Report (Annex 7) ► FLC Certificate (Annex 8) |
|  | Sub-activity 5.3 | The FLC verifies the reports and supporting documents (through the JeMS) |  | - | X |  |  | 60 days | ► The partner's report; ► The subsidy contract; ► Documents to the report | ► IFLC Checklist (Annex 6) ► Independent FLC Report (Annex 7) ► FLC Certificate (Annex 8) |
| Activity 6 Appeal | Sub activity 6.1 | The partner submits the appeal to FLCU. |  |  |  | X |  | 10 working days from receiving the FLC Certificate | ► Appeal by project partner (Annex 10) |  |
|  | Sub activity 6.2 | Following receiving the appeal the Head of FLCU registers the appeal in the Appeals registry, in the same day the appeal was received |  |  | X |  |  |  | ► Appeal by project partner (Annex 11) | ► Annex 11 Appeals registry |
|  | Sub activity 6.3 | The Head of FLCU will designate two controllers for analysing the appeal |  | X | X |  |  | The same day the appeal was received | ► Appeal by project partner (Annex 10) | ► Annex 12 Template for appointment controllers for appeals |
|  | Sub activity 6.3 | The appointed controllers and Head of FLCU will solve the appeal and will inform the partner regarding the resolution |  | X | X |  |  | 10 working days | ► Appeal by project partner (Annex 10) | ► Annex 13 Template for Appeal resolution |