ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting authority

Regional Agency for Socio Economic Development – Banat Ltd., Dr Kornela Radulovića 18, 23000 Zrenjanin, Republic of Serbia

## Country background

The project is implemented within the Interreg IPA Romania-Serbia Programme for the period 2021 - 2027. It lays the foundations for using EU funds under the cross - border component of the IPA Regulation, to support cross - border cooperation on the Romanian - Serbian side.

## Current situation in the sector

The Serbian-Romanian border area has similar problems on both sides of the border. In the ageingsocieties of small rural settlements, development opportunities are limited. These settlements areoften unaware of their natural and cultural assets and lack the capacity to exploit them. Without anystrategic planning on how to capitalise on their natural, cultural assets, these are not recognized asmarketable offers on international markets, and thus fail to become a driving force for the socioeconomicdevelopment of these stagnating areas.

In 2009, the European Parliament asked the Commission and the Member States to consider theEuro Velo-Network and Iron Curtain Trail as an opportunity for promoting European trans-bordercycling infrastructure networks, supporting soft mobility and sustainable tourism. The EuropeanCommission organized workshops to raise awareness of the ICT and awarded grants to preparatoryprojects to define the itinerary and develop overview action plans partly covering the SEE region.

A well-established international cycling route such as EuroVelo 13 represents a major opportunity forthe overall development of a region, and our cross-border area is passed by the Euro Velo 13 route.Within previously implemented projects by both countries, no one has thought about the touristicpotential and economic benefits this area can have in cycle tourism.

## Related programmes and other donor activities

This project is in agreement with European and national trends. It will create a collaborative environment where participants included in the project will show the ability to achieve national and international competitiveness of the cross - border region.

# OBJECTIVES& EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact)to which this action contributes is:Strengthening capacity for the sustainable economic development of the cross-border region throughthe improvement of the cross-border tourist offer and creation of conditions for the development ofcycling tourism.

## Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

The contract will support Regional Agency for Socio Economic Development – Banat Ltd. Zrenjanin, Republic of Serbia, in the process of implementation EU funded project ” Cycling along Iron Curtain Trail - EuroVelo13 in Banat” financed under INTERREG-IPA CBC Romania-Serbia Programme. Contractor is expected to provide consultancy services related to creation of new touristic product.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

Extension of the Tour de Banat route network: development of 5 new Tour de Banatroutes

Research, identification and presentation of local testimonies related to the IronCurtain.

Development of the content of an educational trail on the history and ecosystem of theBega Canal

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Not applicable.

## Risks

Not applicable.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Contractor will be responsible for the following tasks:

In order to increase the attractiveness of the region, and to offer additional tourist packages to EV 13, it is necessary to create complementary destinations that keep tourists in the region for a longer period of time.

In particular Contractor is expected to :

- To develop 5 new cycle routes beside the EV13 – an extension of the Tour de Banat network

- To underlinepotential of region's cultural and naturalresources by creating a thematic route on the IronCurtain theme

- To create content of an educational trail on thehistory and ecosystem of the Bega Canal.

### Geographical area to be covered

The Republic of Serbia, AP Vojvodina, Central Banat district, City of Zrenjanin.

### Target groups

Project stakeholders, government officials, NGOs and other interested parties.

## Specific work

1. Development of 5 new cycling routes in addition to EV13 - as an extension of the Tour de Banat network which will include following actions:

- Survey of current situation

- Survey of current and planned roads/bicycle paths in the area of interest

- Survey for existing attractions, possible rest stops and available relevant services

Contractor will be provided with extensive material by Contracting Authority but need to perform research on its own as well field research.

- Participation in development of action plan

A document will be created containing a detailed analysis of the current situation and concrete proposals, as an action plan, for route and infrastructure development. This will be done by Contracting Authority in cooperation with Local Authorities and Contractor is expected to provide concrete propositions with pros and cons of every action. During this activity exact trace of new cycling routes will be designated.

- Participation in creation of Guide for local service providers

This will be done by Contracting Authority in cooperation with Lead partner and Contractor. It is expected that Contractorparticipates in creation of Guide to be used as a tool for the development and improvement of tourism services related to the EV13 tourism product, outlining the basic conditions to be met by related service providers in order to adapt to the special needs of cyclists; proposals for other necessary services for tourists travelling by bicycle.

- Creation of Signpost and information boards design

In cooperation with Contracting Authority Contractor is expected to create graphic design of all signs and signage layout in a format suitable for production and content for information boards in the field in order to mark extension routes.

- Implementation of IT activities

Contractor is expected to facilitate Extension of the Tour de Banat Routes by modification/updating content and technologyof existing Tour de Banat platforms, (digital maps, inventory of the tourist attractions with texts on 3 languages ​​and photos and updating existing mobile apps and also web content) Update will include: route plans, accessibility, database of tourist attractions and services, signage and information system concept, maps, as well as online presentation etc.

- Cooperation with experts on the Romanian side

Contractor should cooperate and develop the routes together withRomanianexperts. Theywill participate in jointmeetings and joint discussions.

2. Improvement of the cultural and natural resources of the region through the creation of a themed route on the theme of "Iron Curtain";

This will include research, identification and presentation of local testimonies related to the Iron Curtain and creating content by presenting testimonies, stories related to the Iron Curtain in a form suitable for further processing in digital and audio format. It can be made as short videos, or written testimonials with pictures or similar.

3. designing the content of the educational trail dedicated to the history and ecosystem of the Begej canal.

Contractor is expected to develop content of an educational trail on the history and ecosystem of the Bega Canal to be used in the form of an educational trail for young people, to be carried out along the Bega Canal route.Contractor is not only responsible for the design or delivery of the content, but is expected to prepare complete technical documentation that enables the actual implementation for setting up or displaying elements within the educational path. This includes, for example, technical solutions for the infrastructure (how the billboards, info-boards should look, what should be the power supply for the totems, info boards, singsand similar), technical drawings and specifications (dimensions of billboards, info-boards, materials from which to make them, method of assembly, resistance to weather conditions), and the estimate costs of all that. Documents should be prepared on the basis of setting up an educational track. This could be made as book of standards with dimensions, appearance, materials, with a price list, and in line with the requirements of the visibility program.

Important Note

In all phases of its service Contractor is expected to closely cooperate and with approval of Contracting Authority while providing services in line with visibility rules of programme (see http://www.romania-serbia.net ).

## Project management

### Responsible body

The Contractor is responsible for all activities regarding the contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Legal Representative.

### Facilities to be provided by the contracting authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

Zrenjanin, Central Banat District, AP Vojvodina, Republic of Serbia

## Start date &period of implementation of tasks

The intended start date is date of signature of contract by both parties and the period of implementation of the contract will be15 months.Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country,shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped.In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities.It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract.Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English and Serbian language in one original. Printed report or digitally signed with valid certificate are equally acceptable(for environmental reasons)

- Interim Report The contractor will prepare interim reports on the implementation of the tasks, at the 6thmonth and 11th of contract service implementation. The report shall contain a sufficiently detailed description of the different options to support an informed decision on service performed. The interim reports report must be provided along with the corresponding invoice. The approval of the interim report by the Contracting Authority.

- Final report The contractor will prepare final report on the implementation of the tasks, at the end of this contract.The report shall contain a sufficiently detailed description of the different options to support an informed decision on service performed. The final report must be provided along with the corresponding invoice. The approval of the final report by the Contracting Authority will be the basis for issuing final payment as indicated in the Special Conditions.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract.The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is Services provided in timely, quality

and quantity manor as required in these Terms of reference

## Special requirements

Not applicable.