ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Romania

## Contracting authority

Otelek Hungarian for Hungarians Association

## Country background

The Interreg IPA Romania-Serbia Programme was the first Interreg IPA Programme, in the EU, to be approved by the European Commission, on the 19th of July 2022.

The Programme area includes three counties in Romania (Timiș, Caraș-Severin and Mehedinţi), as well as six districts in Serbia (Severno Banatski, Srednje Banatski, Južno Banatski, Braničevski, Borski și Podunavski).

In the 2021-2027 programming period, the Ministry of Development, Public Works and Administration is acting as Managing Authority for the Interreg IPA Romania-Serbia Programme, which will have a total budget of 87.725.681 EUR and will finance projects on environmental protection and adaptation to climate change, healthcare and education, tourism and culture and border management.

The funding for these priorities will be 85% from the Instrument for Pre-Accession assistance (IPA III), 13% Romanian state budget co-financing and 2% as own contribution of the Romanian beneficiaries. Serbian beneficiaries will provide 15% co-financing as their own contribution.

## Current situation in the sector

Tourism plays an important role in the economy of the program area, so stronger cross-border cooperation is crucial for the creation and development of an attractive tourist offer in the region of cross-border cooperation. There are natural resources, cultural and historical assets that should be used to provide much better visibility for tourists. Developing sustainable tourism (adventure tourism) has the capacity to attract visitors to the program area, taking into account that there is a great need to improve poor infrastructure, as well as provide adequate services.

- Identified weaknesses in the cross-border region in terms of tourism are unresolved tourism potentials, lack of competitive products, low standard of accommodation infrastructure, lack of coordinated tourist offers and services, low "digital demand" for tourism in both countries (community visibility on the Internet), lack of competitive tourist products, low competences for product development and marketing, low level of information about tourism trends and support measures and lack of a network with local partners and the tourism industry for the preparation and certification of the quality of tourism products.

## Related programmes and other donor activities

This Project, proposed contract is complementary to other national and programmes financed by the EU.

# OBJECTIVES & EXPECTED OUTPUTS

The project “Development of adventure tourism based on natural values of the Banat region”, acronym Avantur Banat will contribute to the Programme priority specific objective: 2.3 - Enhancing the role of culture and sustainable tourism in economic development, social inclusion and social innovation

## Overall objective

The overall objective (Impact) to which this action contributes is :

The project will contribute to the development and implementation of measures for the development and promotion of adventure tourism, the strategic development of tourism using tourist potential and resources and the implementation of marketing campaigns, as well as the diversification of tourist destinations in the program area, while increasing the accessibility and visibility of less developed tourist areas.

## Specific objective(s)

The  specific objectives (Outcomes) of this contract are as follows:

1. Organizing the education for the rangers and greeters

2. Presentation of the joint adventure tourism offer in the tourism fairs in Romania, Bucharest

3. Organizing the test tours on the elaborated routes in Romanian side

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

Organizing a 50 hours long training with 20 participants – Outcome 1

Organizing the participation at an international touristic fair in Bucharest – Outcome 2

Organizing a 3 days long test tour on the Romanian side of the border for 15 persons – Outcome 3

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The Consultant has to assume the tasks under the project according to the present Terms of Reference and according to the best practices in the field.

## Risks

Not applicable.

# SCOPE OF THE WORK

## General

### Description of the assignment

For details, see point 4.2. Specific work.

### Geographical area to be covered

Timis, Caras and Mehedinti counties, Bucharest, Romania

### Target groups

- 20 participants from Timis county, who will attend the training

- 1000 visitors (general public) to the touristic fair in Bucharest

- 15 participants to the test tour

## Specific work

Activity 1 - Organizing the education for the rangers and greeters

Organizing 50-hour training program in Timis county, with the participation of 20 persons. The training will cover essential tourism, hospitality, guiding, and language skills. It will also include instruction on maintaining equipment purchased through the project.

The Contractor must provide the trainer/trainers with appropriate experience in the adventure tourism sector and in tourism education. Adequate space with teaching equipment (laptop, projector, flip chart) and meals (1 meal per day – catering or restaurant, at least a starter, a soup and a main meal, with at least one vegetarian option and supplementary options for people with different food sensibilities 1 coffee break after 2 hours of training – coffee, tea, mineral water, soft drinks, pastries (200 gr/person)) during the training days.

The contractor will promote the training course and will contact potential participants to assure the 20 participants.

The contractor will cooperate with the Serbian project partners in the elaboration of the training material. The training material will be translated in Romanian language and printed in 25 copies.

The finished work training material needs to include the compulsory visibility elements defined by Interreg-IPA CBC Romania-Serbia Programme.

Budget allocation for activity 1 is: 9000 Eur

Time frame for completion of this task is 6 months, by the end of  November 2026 at the latest.

Activity 2 - Presentation of the joint adventure tourism offer in the tourism fairs in Romania, Bucharest

Organizing a participation at the Bucharest International Tourism Fair in November 2026.

The Contractor will provide the following services:

1. 	REGISTRATION AND LOGISTICS

- Register for the exhibition and reserve booth space min 9 m2

- Review and comply with the organizer’s requirements and deadlines

- Arrange travel, accommodation and meals for 3 persons, 5 nights in Bucharest (hotel at least 3*, single rooms, 3 meals/day)

- Organize transport for exhibition materials to Bucharest

2.	BOOTH DESIGN AND SETUP

- Design an attractive and informative exhibition booth with an exhibition desk and min. 4 chairs

- Prepare banners, posters, and branded materials

- Ensure booth setup complies with venue regulations (electricity, fire safety, etc.)

3. 	MARKETING MATERIALS

- Use the created and printed brochures (at least 300 pieces, 16 pages colour) and flyers (at least 2000 pieces, colour)

- Prepare press kits or media packages (at least 50 pieces)

4. 	Team preparation

- Select and brief booth staff (sales reps, marketers, guides, etc.) min. 1 person

- Prepare product/service presentations and demos

# On-site Execution

- Set up booth on time

- Ensure availability of all marketing materials and products

- Engage actively with visitors and collect contact data

- Take photos and videos for post-event use

The consultant should work closely with the Contracting Authority representatives during the conducting of the work to ensure that the required outputs are properly developed.

The prepared outputs must be delivered in electronic format too.

The marketing materials, have to include the compulsory visibility elements defined by Interreg-IPA CBC Romania-Serbia Programme.

Budget allocation for activity 2 is: 15000 Eur

Time frame for completion of this task is 6 months, by the end of  November 2026 at the latest.

Activity 3 - Organizing the test tours on the elaborated routes in Romanian side

The main goal of this activity is to organise a 3 day test trip on the Romanian side of the area, for tourism professionals, journalists, TDM experts, employees of sales tourism offices, influencers and project management staff of the project from both countries Serbia and Romania. This activity will consist of 3-day events, during which participants will experience all key elements of each itinerary, including attractions and service facilities, at an accelerated pace. The routes for the test tours are provided by the contracting authority.

The Contractor ensure accommodation for 15 persons for two nights (single rooms, at least 3* hotel).

The Contractor ensure travelling for 15 participants with minibus for 3-day. The total distance of the travelling is approximately 500 km, in the territory of Timis, Caraș and Mehedinți counties. The trip will start from Otelec. Also if needed the contractor will assure the travel to and from Otelec from Timis county and Voivodina (Serbia) for a distance of maximum 300 km/person. Meals for 15 participants (first day lunch and dinner, second day breakfast, lunch and dinner, third day breakfast and lunch) will be provided by the Contractor. Ensure that they can try out the adventure tourism elements that are developed before, during the activities of the project and they are part of the adventure tour itineraries on the Romanian side. The service will include the price of the selected  attractions. The contractor will assure the documentation of the trip (at least 50 photos).

Budget allocation for activity 3 is: 9000 Eur

Time frame for completion of this task is between June-October 2026.

## Project management

### Responsible body

The Contractor is responsible for all the activities regarding this contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the case of the Beneficiary is Kozma Stefan, Legal Representative.

### Facilities to be provided by the contracting authority and/or other parties

The Beneficiary will provide office space with an internet connection for the facilitation of this service if required by the Contractor.

# LOGISTICS AND TIMING

## Location

Tasks related to this contract will be implemented in Otelec, Timis county, Vest Region, Romania, Bucharest, Caraș and Mehedinți counties.

## Start date & period of implementation of tasks

The intended start date is 20.05.2026 and the period of implementation of the contract will be until 20.12.2026. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and 1 copies:

- Interim reports before requesting interim payments. For both Lot the Contractor has the possibility to request interim payments, after finishing some activities.

Final report at the end of the contract, upon all contract results have been achieved. The approval of the final report by the Contracting Authority will be the basis for issuing final payment as indicated in the Special Conditions. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manor, as required in these Terms of Reference”.

## Special requirements

Not applicable